## Tracker
Jet Ski Product Page: Progress Tracker
Same 27 items as the Word document. Edit only the yellow cells (Status, Checked, Notes). Everything in the summary updates by itself.
Overall progress | Count | By group | Items | Done | Needs review
Items | 27 | Pages: build to final KoverUI standard | 11 | 0 | 0
Not started | 27 | Look and feel | 3 | 0 | 0
In progress | 0 | Make it real (mockup fakes these today) | 8 | 0 | 0
Needs review | 0 | Decisions and rules to settle | 5 | 0 | 0
Can't be done | 0
Done | 0
% Done | 0%
% Checked (verified) | 0%
Progress bar (Done) | ░░░░░░░░░░░░░░░░░░░░
Legend: yellow cells are for you to fill in. 🔒 = deliberate design choice, check with us before changing.
# | Group | Item | 🔒 Intentional | Status | Checked | Notes / who / what we need to review | Section in Word
1 | Pages: build to final KoverUI standard | Intro and duty acknowledgement | Yes | Not started | No |  | Section 4.1
2 | Pages: build to final KoverUI standard | Target Market Determination and decline |  | Not started | No |  | Section 4.2
3 | Pages: build to final KoverUI standard | PWC / Jet Ski Details fields and conditional questions | Yes | Not started | No |  | Section 4.3
4 | Pages: build to final KoverUI standard | Owners and skippers block | Yes | Not started | No |  | Section 4.3
5 | Pages: build to final KoverUI standard | Additional PWC / Jet Ski units | Yes | Not started | No |  | Section 4.4
6 | Pages: build to final KoverUI standard | History questions and claims table | Yes | Not started | No |  | Section 4.5
7 | Pages: build to final KoverUI standard | Your Quote layout, cover and summaries | Yes | Not started | No |  | Section 4.6
8 | Pages: build to final KoverUI standard | Referral and Email Quote modals | Yes | Not started | No |  | Section 4.6
9 | Pages: build to final KoverUI standard | Your Details, identification, trailers, attachments |  | Not started | No |  | Section 4.7
10 | Pages: build to final KoverUI standard | Payment: method and card entry | Yes | Not started | No |  | Section 4.8
11 | Pages: build to final KoverUI standard | Confirmation and documents | Yes | Not started | No |  | Section 4.9
12 | Look and feel | Design system: palette, progress bar, ticks, panels | Yes | Not started | No |  | Section 1
13 | Look and feel | Searchable dropdowns, dates, currency and length inputs | Yes | Not started | No |  | Section 1
14 | Look and feel | Responsive, accessibility and browser testing |  | Not started | No |  | Section 1
15 | Make it real (mockup fakes these today) | Switch validation on (remove DEV_BYPASS_VALIDATION) |  | Not started | No |  | Section 6
16 | Make it real (mockup fakes these today) | Rating engine and per-unit pricing |  | Not started | No |  | Section 6
17 | Make it real (mockup fakes these today) | Address lookup |  | Not started | No |  | Section 6
18 | Make it real (mockup fakes these today) | Quote number, save and resume |  | Not started | No |  | Section 6
19 | Make it real (mockup fakes these today) | Email: quote and referral |  | Not started | No |  | Section 6
20 | Make it real (mockup fakes these today) | PDS, FSG, receipt, Certificate of Currency |  | Not started | No |  | Section 6
21 | Make it real (mockup fakes these today) | Payment gateway and surcharge fix |  | Not started | No |  | Section 6
22 | Make it real (mockup fakes these today) | File uploads and sign-in |  | Not started | No |  | Section 6
23 | Decisions and rules to settle | Full TMD decline rule set |  | Not started | No |  | Section 7
24 | Decisions and rules to settle | History answers: referral or decline? |  | Not started | No |  | Section 7
25 | Decisions and rules to settle | Skipper age and experience rules |  | Not started | No |  | Section 7
26 | Decisions and rules to settle | Instalments: the $172.31 gap |  | Not started | No |  | Section 7
27 | Decisions and rules to settle | Wording fixes (TMD "Vessel(s)", typo) |  | Not started | No |  | Section 7